|  | OVERVIEW OF NEW PROVINCIAL JAIL INFRASTRUCTURE PROJECTS IN ONTARIO SINCE THE FORD GOVERNMENT TOOK OFFICE (June 2018 – present) Prepared by: Justin Piché, PhD – Full Professor, Criminology, University of Ottawa Date Created ¦ Last Updated: 8 September 2025 ¦ 13 April 2026 Contact: justin.piche@uottawa.ca |  |
| --- | --- | --- |

| Project and Location | Additional Beds (cost to build per bed) | Population(s) | Estimated Construction Cost (project type) | Estimated Annual Operating Cost | Current Project Phase | Project Initiation and Substantial Completion Dates (total project time) |
| --- | --- | --- | --- | --- | --- | --- |
| Kenora Jail – expansion (Treaty 3 Territory / Kenora) | 50 (960k per bed) | Men and Women | $96 million (accelerated build program) | $6.5 million ($357/day per prisoner) | Completed | 14 July 2020 – 28 September 2022 (2 years, 2.5 months) |
| Thunder Bay Correctional Centre – expansion (Robinson-Superior Treaty Territory / Thunder Bay) | 50 (960k per bed) | Men |  | $6.5 million ($357/day per prisoner) | Completed | 14 July 2020 – 28 September 2022 (2 years, 2.5 months) |
| Elgin-Middlesex Detention Centre – intermittent centre retrofit (Anishinaabek, Haudenosaunee, Lūnaapéewak and Attawandaron Territory / London) | 110 | Men and Women | Undisclosed | $14.3 million ($357/day per prisoner) | Completed | 10 June 2024 – 21 March 2025 (2 years, 2.25 months) |
| Toronto South Detention Centre – intermittent centre retrofit (Wendat, Anishnaabeg and Haudenosaunee Territory / Toronto) | 320 | Men | Undisclosed | $41.7 million ($357/day per prisoner) | Construction | 10 June 2024 – 2026 (projected at 1 year + at least 6 months) |
| Thunder Bay Correctional Complex – new facility * (Robinson-Superior Treaty Territory / Thunder Bay) | 345 ($3.5M per bed) | Men and Women | $1.2 billion (design, build, finance, maintain) | $45 million ($357/day per prisoner) | Construction | 4 May 2017 – Fall 2026 (projected at 9 years, 4 months) |
| Niagara Detention Centre – expansion (Anishinaabeg and Haudenosaunee Territory / Thorold) | 50 ($1.2M per bed) | Men | $180 million (modular build facilities) | $6.5 million ($357/day per prisoner) | Contract Awarded / Construction Planned for 2026 | 16 July 2025 – Fall 2027 (projected at 2 years + at least 2 months) |
| Vanier Centre for Women – expansion (Territory of the Mississaugas of the Credit First Nation / Milton) | 50 ($1.2M per bed) | Women |  | $6.5 million ($357/day per prisoner) |  | 16 July 2025 – Winter 2028 (projected at 2 years + at least 5 months) |
| Cecil Facer Youth Centre – expansion and conversion into a women’s jail (Robinson-Superior Treaty Territory / Atikameksheng Anishnaabeg Territory / Sudbury) | 50 ($1.2M per bed) | Women |  | $6.5 million ($357/day per prisoner) |  | 9 February 2023 – 2028 (projected at 4 years + at least 2.5 months) |
| Quinte Detention Centre – expansion and retrofit (Wendat, Anishinaabeg and Haudenosaunee Territory / Napanee) | 91 (per bed cost TBA) | Women | Up to $499 million (design, bid, build) | $11.9 million ($357/day per prisoner) | Request for Proposals | 27 August 2020 – May 2029 (projected at 8 years, 8 months) |
| New Brockville Correctional Complex – new facility (Wendat, Anishinaabeg and Haudenosaunee Territory / Brockville) | 270 (per bed cost TBA) | Men | Up to $499 million (design, bid, build) | $35.2 million ($357/day per prisoner) | Request for Qualifications | 27 August 2020 – May 2031 (projected at 10 years, 8 months) |
| St. Lawrence Valley Correctional and Treatment Centre – expansion (Wendat, Anishinaabeg and Haudenosaunee Territory / Brockville) | 25 (per bed cost TBA) | Women |  | $3.3 million ($357/day per prisoner) |  |  |
| Eastern Ontario Correctional Complex – new facility (Algonquin Territory / Kemptville) | 235 (per bed cost TBA) | Men and Women | Up to $499 million (design, build, finance) | $30.6 million ($357/day per prisoner) | Planning / Pre-procurement | 27 August 2020 – November 2032 (projected at 12 years, 3 months) |
| * Note: Upon taking office, the Ford government reviewed a plan first announced by the Wynne government in May 2017 to build the Thunder Bay Correctional Complex. It announced it was moving forward with the project in April 2019. | 1,646 beds |  | Up to $2.97B (announced to date) | $214.5 million per year * Estimated based on 2023/2024 figures published by Statistics Canada (2025), table 35-10-0013-01 |  |  |