|  | OVERVIEW OF NEW PROVINCIAL JAIL INFRASTRUCTURE EXPANSION PROJECTS IN ONTARIO SINCE THE FORD GOVERNMENT TOOK OFFICE (June 2018 – present) Prepared by: Justin Piché, PhD – Full Professor, Criminology, University of Ottawa Date Created ¦ Last Updated: 8 September 2025 ¦ 15 May 2026 Contact: justin.piche@uottawa.ca |  |
| --- | --- | --- |

| Project and Location | Additional Beds (cost to build per bed) | Population(s) | Announced Construction Cost (project type) | Estimated Additional Construction Cost (where comparators exist) | Estimated Annual Operating Cost | Current Project Phase | Project Initiation and Substantial Completion Dates (total project time) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kenora Jail – expansion (Treaty 3 Territory / Kenora) | 50 (960k per bed) | Men and Women | $96 million (modular build facilities via accelerated build program) |  | $6.5 million | Completed | 14 July 2020 – 28 September 2022 (2 years + 2.5 months) |
| Thunder Bay Correctional Centre – expansion (Robinson-Superior Treaty Territory / Thunder Bay) | 50 (960k per bed) | Men |  |  | $6.5 million | Completed | 14 July 2020 – 28 September 2022 (2 years + 2.5 months) |
| Elgin-Middlesex Detention Centre – intermittent centre retrofit (Anishinaabek, Haudenosaunee, Lūnaapéewak and Attawandaron Territory / London) | 110 | Men | Undisclosed |  | $14.3 million | Completed | 10 June 2024 – 21 March 2025 (2 years, 2.25 months) |
| Toronto South Detention Centre – intermittent centre retrofit (Wendat, Anishnaabeg and Haudenosaunee Territory / Toronto) | 320 | Men | Undisclosed |  | $41.7 million | Construction | 10 June 2024 – December 2026 (projected at 1 year + 6 months) |
| Central East Correctional Centre – expansion (Michi Saagiig Nichnaabeg Territory / Lindsay) | 122 (per bed cost TBA) | Men | Undisclosed cost (tensile membrane structure) | $11.3 million (based on $8.5 million cost to build London Intermittent Centre + inflation) | $15.9 million | Planning | 14 May 2026 – December 2026 (projected at 6.5 months) |
| Central North Correctional Centre – expansion (Williams Treaties First Nations Territory / Penetanguishene) | 122 (per bed cost TBA) | Men | Undisclosed cost (tensile membrane structure) | $11.3 million (based on $8.5 million cost to build London Intermittent Centre + inflation) | $15.9 million | Planning | 14 May 2026 – March 2027 (projected at 9.5 months) |
| Location to be announced 1 | 122 (per bed cost TBA) | Undisclosed | Undisclosed cost (tensile membrane structure) | $11.3 million (based on $8.5 million cost to build London Intermittent Centre + inflation) | $15.9 million | Planning | 14 May 2026 – December 2027 (projected at 1 years + 6 months) |
| Location to be announced 2 | 122 (per bed cost TBA) | Undisclosed | Undisclosed cost (tensile membrane structure) | $11.3 million (based on $8.5 million cost to build London Intermittent Centre + inflation) | $15.9 million | Planning | 14 May 2026 – December 2027 (projected at 1 years + 6 months) |
| Location to be announced 3 | 122 (per bed cost TBA) | Undisclosed | Undisclosed cost (tensile membrane structure) | $11.3 million (based on $8.5 million cost to build London Intermittent Centre + inflation) | $15.9 million | Planning | 14 May 2026 – December 2027 (projected at 1 years + 6 months) |
| Thunder Bay Correctional Complex – new facility * (Robinson-Superior Treaty Territory / Thunder Bay) | 345 + 117 (per bed cost TBA) | Men and Women | $1.2 billion (design, build, finance, maintain) | + undisclosed cost for change in scope announced on 14 May 2026 | $60.2 million | Construction | 4 May 2017 – June 2027 (projected at 10 years, 1 month) |
| Cecil Facer Youth Centre – expansion and conversion into a women’s jail (Robinson-Superior Treaty Territory / Atikameksheng Anishnaabeg Territory / Sudbury) | 50 + 50 (per bed cost TBA) | Women | $180 million (modular build facilities) | + undisclosed cost for change in scope (i.e. “doubling the occupancy of each cell” and related upgrades) announced on 14 May 2026 | $13 million | Contract Awarded / Construction Planned for 2026 | 9 February 2023 – March 2028 (projected at 5 years + 0.75 months) |
| Niagara Detention Centre – expansion (Anishinaabeg and Haudenosaunee Territory / Thorold) | 50 + 50 (per bed cost TBA) | Men |  |  | $13 million |  | 16 July 2025 – June 2028 (projected at 2 years + 10 months) |
| Vanier Centre for Women – expansion (Territory of the Mississaugas of the Credit First Nation / Milton) | 50 + 50 (per bed cost TBA) | Women |  |  | $13 million |  | 16 July 2025 – June 2028 (projected at 2 years + 10 months) |
| Quinte Detention Centre – expansion and retrofit (Wendat, Anishinaabeg and Haudenosaunee Territory / Napanee) | 91 (per bed cost TBA) | Women | Up to $499 million (design, bid, build) |  | $11.9 million | Request for Proposals | 27 August 2020 – August 2029 (projected at 9 years) |
| New Brockville Correctional Complex – new facility (Wendat, Anishinaabeg and Haudenosaunee Territory / Brockville) | 270 (per bed cost TBA) | Men | Up to $499 million (design, bid, build) |  | $35.2 million | Request for Qualifications | 27 August 2020 – May 2031 (projected at 10 years, 8 months) |
| St. Lawrence Valley Correctional and Treatment Centre – expansion (Wendat, Anishinaabeg and Haudenosaunee Territory / Brockville) | 25 (per bed cost TBA) | Women |  |  | $3.3 million |  |  |
| Eastern Ontario Correctional Complex – new facility (Algonquin Territory / Kemptville) | 235 (per bed cost TBA) | Men and Women | Up to $499 million (design, build, finance) |  | $30.6 million | Planning / Pre-procurement | 27 August 2020 – November 2032 (projected at 12 years, 3 months) |
| * Note: Upon taking office, the Ford government reviewed a plan first announced by the Wynne government in May 2017 to build the Thunder Bay Correctional Complex. It announced it was moving forward with the project in April 2019. | 2,523 beds |  | Up to $2.97B (announced to date) | At least another $56.5 million | At least $328.8 million per year by 2033 * Estimated based on 2023/2024 cost of $357 per day published by Statistics Canada (2025) table 35-10-0013-01 |  |  |